## Sheet1
Date | Duration (hrs) | Task | Comments
2023-09-10 | 3:00 | Creating Design Document | The design was the easiest part since the app I am making already exists. Hardest part was figuring out Figma and making the user flow chart.
2023-09-11 | 2:00 | Setting up Xcode | Had to set up Xcode on a virtual device since I don't own a Mac
2023-09-13 | 4:00 | Learning Xcode | Although I had used Xcode before for some projects I was involved in, I never used it to make an app from scratch myself. Figured before I did anything I should learn how to use it properly with some guides and videos.
2023-09-14 | 5:00 | Set up new workstation | I, alongside my friend, was using this monthly service called macincloud since neither of us owned a Mac which we needed for some projects. The servers stopped working and I wasn't able to connect to the remote desktop. We decided to invest in a Mac Mini so i spent the day getting that and setting it up.
2023-09-16 | 1:30 | Tried setting up GitHub | I made an account and had no idea what to do after that, decided to ask AJ on campus if he can help me. I was also able to contact my friend's dad who's a retired programmer and he agreed to be my supervisor.
2023-09-18 | 0:45 | Set up Git | Downloaded Git, still have no idea what it is or what to do with it. I realized I can just add the xlsx file to my GitHub repository so I am hoping that's correct
2023-09-22 | 2:30 | Started working on the app | Started working on the main page with the balance. So far getting the hang of Xcode. Got the top of the page icons complete as well as the logo in the middle.
2023-09-24 | 3 | Learning how to use "buttons" | Making buttons to bring up other screens in Xcode was more challanging than I thought so I spent quite some time reading and watching videos on how they work.
2023-09-25 | 1 | Debugging | Main page kept showing a black recangle on the top of the screen and I couldn't figure out where the Zstack should go in the code.
2023-09-27 | 1:30 | Greeting message | The greeting message on the main screen has to say good morning, afternoon, and evening based on time of day. I was able to figoure out how to make it behave like that.
2023-09-29 | 2 | Navigation | I was able to make the buttons be able to take the user to the corresponding page. Finding the fucntion to do that wasn't the issue but it kept resizing everything and I spent a while figuring that out. Turns out I had an extra "Spacer()" written and an extra "}"