## Sheet1
Date | Duration (hrs) | Task | Comments
2023-09-10 | 3:00 | Creating Design Document | The design was the easiest part since the app I am making already exists. Hardest part was figuring out Figma and making the user flow chart.
2023-09-11 | 2:00 | Setting up Xcode | Had to set up Xcode on a virtual device since I don't own a Mac
2023-09-13 | 4:00 | Learning Xcode | Although I had used Xcode before for some projects I was involved in, I never used it to make an app from scratch myself. Figured before I did anything I should learn how to use it properly with some guides and videos.
2023-09-14 | 5:00 | Set up new workstation | I, alongside my friend, was using this monthly service called macincloud since neither of us owned a Mac which we needed for some projects. The servers stopped working and I wasn't able to connect to the remote desktop. We decided to invest in a Mac Mini so i spent the day getting that and setting it up.
2023-09-16 | 1:30 | Tried setting up GitHub | I made an account and had no idea what to do after that, decided to ask AJ on campus if he can help me. I was also able to contact my friend's dad who's a retired programmer and he agreed to be my supervisor.
2023-09-18 | 0:45 | Set up Git | Downloaded Git, still have no idea what it is or what to do with it. I realized I can just add the xlsx file to my GitHub repository so I am hoping that's correct