## Sheet1
Date | Duration (hrs) | Task | Description
2023-09-10 | 3:00 | Creating Design Document | The design was the easiest part since the app I am making already exists. Hardest part was figuring out Figma and making the user flow chart.
2023-09-11 | 2:00 | Setting up Xcode | Had to set up Xcode on a virtual device since I don't own a Mac
2023-09-13 | 4:00 | Learning Xcode | Although I had used Xcode before for some projects I was involved in, I never used it to make an app from scratch myself. Figured before I did anything I should learn how to use it properly with some guides and videos.
2023-09-14 | 5:00 | Set up new workstation | I, alongside my friend, was using this monthly service called macincloud since neither of us owned a Mac which we needed for some projects. The servers stopped working and I wasn't able to connect to the remote desktop. We decided to invest in a Mac Mini so i spent the day getting that and setting it up.
2023-09-16 | 1:30 | Tried setting up GitHub | I made an account and had no idea what to do after that, decided to ask AJ on campus if he can help me. I was also able to contact my friend's dad who's a retired programmer and he agreed to be my supervisor.
2023-09-18 | 0:45 | Set up Git | Downloaded Git, still have no idea what it is or what to do with it. I realized I can just add the xlsx file to my GitHub repository so I am hoping that's correct
2023-09-22 | 2:30 | Started working on the app | Started working on the main page with the balance. So far getting the hang of Xcode. Got the top of the page icons complete as well as the logo in the middle.
2023-09-24 | 3 | Learning how to use "buttons" | Making buttons to bring up other screens in Xcode was more challanging than I thought so I spent quite some time reading and watching videos on how they work.
2023-09-25 | 1 | Debugging | Main page kept showing a black recangle on the top of the screen and I couldn't figure out where the Zstack should go in the code.
2023-09-27 | 1:30 | Greeting message | The greeting message on the main screen has to say good morning, afternoon, and evening based on time of day. I was able to figoure out how to make it behave like that.
2023-09-29 | 2 | Navigation | I was able to make the buttons be able to take the user to the corresponding page. Finding the fucntion to do that wasn't the issue but it kept resizing everything and I spent a while figuring that out. Turns out I had an extra "Spacer()" written and an extra "}"
2023-10-17 | 1:30 | Research | I needed to implement a tab on the bottom of the screen with buttons that take you to different screens. Those screens don't need to do anything but I still need that tab there. CodeWithChris on YouTube does great tutorials on Xcode functionalities.
2023-10-17 | 2 | Implementing the "TabView" | Actually a lot easier than what was shown in videos. It's all built into Xcode so all I had to do was just call the TabView function and put all the buttons I wanted in ".tabItem" along with the text and Xcode just automatically puts the text under the image for each item. Annoyingly i couldn't name the view "TabView" so i just named it "MainView" since TabView is already a built in Xcode function.
2023-10-18 | 0:35 | Research on Xcode | Watched a couple of videos on tips and tricks on Xcode because there's times I need a certain option or open a setting and I can't find it because I don't know everything about the program.
2023-10-18 | 5 | Finishing the homePage | All that was left for homePage is figure out how to design card stacks. It was getting too messy doing it all in homePageView so I decided to make another view called CardView and just make the card in there and in homePageView just write CardView to put it in the home page. The reason it took so long is i didn't know how to bring up the preview on the right and i had to kep going back and forth between homePageView and CardView to see what i was doing.
2023-10-19 | 2 | Research on menus in Xcode | I noticed that the sending page had some parts to it that I didn't know how to do like the blue rectangle that moves to which tab is selected.
2023-10-19 | 3:30 | Worked on Send and Deposit pages | Started working on the send pagePageView but realized it was more difficult than I thought so I decided to finish the depositPageView first and save the harder and more time consuming things for last.
2023-10-20 | 2 | Finished the Deposit page | The main thing was changing the default back button to the "cancel" on the right side. After some research I as able to figure out that where I put the NavigationLink, I had to add a line that hides the back button.
2023-10-20 | 3 | Went back to finish Send page | What I had left for the sendPageView was to transition between "Pay" and "Payments due" tabs. My friend helped me by showing me how if I create a var and set it to 0 I can later set that variable equal to 1 or 0 depending on which tab is selected. It's just one big if/else statement.
2023-10-24 | 1:30 | Small details | Added some animations to the tab select on the sendPageView. Fixed some spelling and colors that weren't showing up in the simulation.
2023-11-01 | 0:45 | Looked over the code | Looked over everything made sure everything worked in the simulation and nothing was overlapping or anything.